## Sheet1
Task | Days Since Start | Days Left for Completion
Developers need to learn how to use JFreeChart, mySQL, the Apache Commons Math Library, the Java Swing Framework |  | 3
User needs to be able to connect to a database | 3 | 1
User needs to be able to load data from a database, and see a table containing that data | 5 | 4
Test Cases for Use Case 1 | 8 | 2
User needs to be able to switch between seeing raw data, and seeing descriptive statistics of the data | 10 | 3
Test Cases for Use Case 2 | 13 | 2
User needs to be able to choose between different visualizations | 15 | 5
Test Cases for Use Case 3 | 20 | 4
User needs to be able to compare two time-series with a statistical test | 24 | 6
Test Cases for Use Case 4 | 30 | 6
Refactor Code | 36 | 7
User needs to be able to predict the next X months of a given time-series | 43 | 7
Test Cases for Use Case 5 | 50 | 7